## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Team member name | Status
Sprint 1 | Sprint 1 | US-01 | Gather heathcare Datasets from internett souces and also created synthetic datasets | MUST HAVE | Dataset availability | Mandavi | Completed
Sprint 1 | Sprint 1 | US-02 | performed data preprocessing steps like data cleaning and EDA | MUST HAVE | Raw data | Mandavi | Completed
Sprint 1 | Sprint 1 | US-03 | processed multiple datasets for multiple features as per the project needs. | MUST HAVE | cleaned data | Mandavi | Completed
Sprint 2 | Sprint 2 | US-04 | Review the formulas and KPI to monitor Hospital finalcial and Managment data | MUST HAVE | Data cleaning, KPI calculation | Mandavi | Completed
Sprint 2 | Sprint 2 | US-05 | Integrating several Healthcare feature at single dashboard | MUST HAVE | Streamlit and python libraries | Mandavi | Completed
Sprint 2 | Sprint 2 | US-06 | Analyze claim trends within departments to detect problem areas | MUST HAVE | data and trend analysis | Mandavi | Completed
Sprint 3 | Sprint 3 | US-07 | Work on Designing the Dashboard and Creating interactive and informative visuals | MUST HAVE | Matplot, plotly and streamlit | Mandavi | Completed
Sprint 3 | Sprint 3 | US-08 | Dtetailed analysis of KPIs across all departments to support strategic decisions | MUST HAVE | All KPI calculations | Mandavi | Completed
Sprint 3 | Sprint 3 | US-09 | Visualize data through dashboards, charts, and KPIs for easy interpretation | MUST HAVE | Matplot, ploty & Streamlit integration | Mandavi | Completed
Sprint 3 | Sprint 3 | US-10 | Apply filters across each departement to perform detailed analysis | SHOULD HAVE | Dashboard UI components | Mandavi | Completed
Sprint 3 | Sprint 3 | US-11 | Tested the healthcare dashboard on various paramenters and datasets for better results | SHOULD HAVE | data and performance analysis | Mandavi | Completed
Sprint 3 | Sprint 3 | US-13 | started final changes in visulas and overall visuals of the Dashboard | MUST HAVE | plotly , matplot and streamlit | Mandavi | Completed
Sprint 4 | Sprint 4 | US-14 | Final Testing and deployment of the healthcare dashboard | MUST HAVE | Data ,model performance and streamlit | Mandavi | Completed
Sprint 4 | Sprint 4 | US-15 | Tested the healthcare dashboard on various paramenters and datasets for better results | MUST HAVE | streamlit , data and requirement | Mandavi | Completed
Sprint 4 | Sprint 4 | US-17 | Final Testing and deployment of the healthcare dashboard | MUST HAVE | streamlit built-in feature | Mandavi | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Bakclog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 49.5 | 5 | 7 | 9.5 | 10 | 7.5 | 6 | 3.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TASK-001 | Collect hospital dataset and understand columns | 2026-02-06 | 2026-02-07 | Everyone | Data Gathering | Completed | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-002 | Check data types and structure | 2026-02-07 | 2026-02-08 | Everyone | Data Validation | Completed | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-003 | adding multiple coulmns for specific features | 2026-02-08 | 2026-02-09 | Everyone | Data Cleaning | Completed | 1.5 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-004 | Prepare multiple dataset for specif features | 2026-02-09 | 2026-02-10 | Everyone | Data Preprocessing | Completed | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-005 | Basic EDA | 2026-02-11 | 2026-02-12 | Everyone | EDA | Completed | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-001 | TASK-006 | Data analysis and logic building | 2026-02-13 | 2026-02-15 | Everyone | Model Development | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-007 | Changing the dashboard as per project need | 2026-02-15 | 2026-02-16 | Everyone | Model Evaluation | Completed | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-008 | Verifying the changed formulas with datasets | 2026-02-16 | 2026-02-17 | Everyone | Cross verification | Completed | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-009 | adding graphs for different analysis | 2026-02-17 | 2026-02-18 | Everyone | visual analysis | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-010 | Calculate financial KPIs | 2026-02-18 | 2026-02-19 | Everyone | Data Engineering | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-001 | TASK-011 | Designing Dashboard and Integrating features | 2026-02-20 | 2026-02-21 | Everyone | Frontend | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-012 | Add navigation and sidebar | 2026-02-21 | 2026-02-22 | Everyone | Frontend | Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-013 | Add patient dashboard | 2026-02-22 | 2026-02-24 | Everyone | Dashboard | Completed | 3 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-014 | Added KPI's | 2026-02-24 | 2026-02-26 | Everyone | Dashboard | Completed | 2.5 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-015 | Added camparision graph as per needs | 2026-02-26 | 2026-02-28 | Everyone | Dashboard | Completed | 2.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TASK-016 | CFO dashboard and insights | 2026-03-01 | 2026-03-03 | Everyone | Dashboard | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TASK-017 | Add insurance analytics | 2026-03-03 | 2026-03-05 | Everyone | Dashboard | Completed | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TASK-018 | Add PDF export feature | 2026-03-05 | 2026-03-06 | Everyone | Feature | Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TASK-019 | Improve UI and styling | 2026-03-06 | 2026-03-08 | Everyone | Styling | Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-001 | TASK-020 | Added All features at single dashboard | 2026-03-09 | 2026-03-12 | Everyone | Integration | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-021 | Fix bugs and improve filters | 2026-03-12 | 2026-03-14 | Everyone | Debugging | Completed | 2.5 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-022 | Final testing of all features | 2026-03-15 | 2026-03-20 | Everyone | Testing | Completed | 2.5 | 0 | 0 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-023 | Prepare documentation & presentation | 2026-03-20 | 2026-03-24 | Everyone | Documentation | Completed | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Standup Meetings
Sprint | Day | Impediments | Action Taken
S1 | Day 2 | Lack of understending about project | Discussed with mentor in review meeting and finalized problem statement and approach
S1 | Day 5 | Problem in handling large datasets | Optimized data loading using pandas settings and handled data in smaller chunks
S2 | Day 9 | difficulty in referring to different features | Cleaned dataset and created multiple datasets all refrencing to each other
S3 | Day 16 | Isuue with integrating the different features | Discussed with teammates and take reference from external sources
S3 | Day 22 | Charts were not displayed clearly and layout looked cluttered | Improved UI by restructuring chart placement and adding proper titles
S4 | Day 28 | Facing issue with integrating all the features | Debugging code and optimized overall dashboard

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-03-02 | 2026-03-08 | Ankit kumar | Exploring datasets | Time waste in watching turorials | continue working on project | Crawled internet and also tried creating synthethic dataset
2 | S2 | 2026-03-09 | 2026-03-15 | Ankit kumar | data cleaning and processing | procastination | advancing relevent skills | Explores data cleaning methods and processe the datasets
3 | S3 | 2026-03-16 | 2026-03-22 | Ankit kumar | DashBoard development | Wasting time in documentation | Gaining familiarity with tools | developed dashboard using python and streamlit
4 | S4 | 2026-03-23 | 2026-03-26 | Ankit kumar | Intergating all features and testing and ppt making | adding irrelevent features | Maintaining workflow | integrated many features and worked on intractive styles and visulas