## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a hospital admin, I want to upload messy Excel files easily so the system doesn't break. | MUST HAVE | None | Ishwar | Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want a clean and dark-themed screen so it is easy to read. | MUST HAVE | US-01 | Ishwar | Completed
Sprint 1 | Sprint 1 | US-03 | As a manager, I want to see summary cards (like total patients) so I can check hospital status quickly. | MUST HAVE | US-01 | Ishwar | Completed
Sprint 2 | Sprint 2 | US-04 | As a nurse, I want a Ward Capacity page to see how many beds are empty right now. | MUST HAVE | US-02 | Ishwar | Completed
Sprint 2 | Sprint 2 | US-05 | As a dispatcher, I want a MedEvac page to see which hospital can take new ambulance patients. | MUST HAVE | US-04 | Ishwar | Completed
Sprint 2 | Sprint 2 | US-06 | As a user, I want the system to save my actions so I don't lose data if I accidentally refresh the page. | MUST HAVE | US-05 | Ishwar | Completed
Sprint 3 | Sprint 3 | US-07 | As an analyst, I want charts showing patient ages and stay times to understand hospital trends. | MUST HAVE | US-01 | Ishwar | Completed
Sprint 3 | Sprint 3 | US-08 | As a planner, I want a tool that guesses future patient numbers so we can schedule enough staff. | SHOULD HAVE | US-07 | Ishwar | Completed
Sprint 4 | Sprint 4 | US-09 | As a tester, I want to fix overlapping text and chart colors so the final product looks professional. | MUST HAVE | US-07 | Ishwar | Completed
Sprint 4 | Sprint 4 | US-10 | As a student, I want to create a simple guide and picture of how the system works for my final project. | MUST HAVE | None | Ishwar | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Est. Effort (Hrs)
US-01 | TASK-01 | Write code to read the hospital Excel file quickly. | 2026-03-02 | 2026-03-03 | Ishwar | Coding | Completed | 4
US-01 | TASK-02 | Make the code smart enough to fix bad column names automatically. | 2026-03-03 | 2026-03-04 | Ishwar | Coding | Completed | 3
US-02 | TASK-03 | Add colors and styles to make the dashboard look modern. | 2026-03-04 | 2026-03-05 | Ishwar | Design | Completed | 5
US-06 | TASK-04 | Create a save feature so ambulance dispatches aren't lost on refresh. | 2026-03-10 | 2026-03-11 | Ishwar | Coding | Completed | 6
US-07 | TASK-05 | Build charts for Patient Analytics (like a pie chart for departments). | 2026-03-15 | 2026-03-16 | Ishwar | Design | Completed | 4
US-09 | TASK-06 | Fix the bug where chart labels were hiding behind each other. | 2026-03-24 | 2026-03-24 | Ishwar | Bug Fix | Completed | 2
US-09 | TASK-07 | Fix the screen showing raw code text instead of proper titles. | 2026-03-25 | 2026-03-25 | Ishwar | Bug Fix | Completed | 1

## Stand-up Meeting
Sprint | Day | Impediments (What went wrong) | Action Taken (How we fixed it)
S1 | Day 2 | The Excel file was crashing the app because it had weird spaces in the titles. | Wrote a script to clean up the words and remove extra spaces before loading.
S2 | Day 6 | When sending an ambulance, the data disappeared if we refreshed the screen. | Created a local save file so the system remembers what we did even after a reload.
S3 | Day 11 | The background colors on some charts were too dark and hard to read. | Changed the color settings to make the charts slightly see-through and brighter.
S3 | Day 13 | The names of the hospital departments were too long and overlapping on the pie chart. | Moved the text labels to the outside of the chart and added more space around them.
S4 | Day 15 | The section titles were accidentally showing programming code on the screen. | Changed the way the text was written in the code to force it to show up as normal words.

## Retrospection
Sprint # | Sprint Start | Sprint End | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
S1 | 2026-03-02 | 2026-03-08 | Mandavi Vaishya | Putting different parts of the app into separate files. | Putting all the code into one giant file that is hard to read. | Making sure the app loads fast. | Split the code into a "Dashboard" file and a "Data" file.
S2 | 2026-03-09 | 2026-03-15 | Mandavi Vaishya | Writing code that handles mistakes gracefully. | Assuming the Excel file will always be typed perfectly. | Building features that update in real-time. | Added a "safe check" feature to handle spelling mistakes in the data.
S3 | 2026-03-16 | 2026-03-22 | Mandavi Vaishya | Checking how the charts look on smaller screens. | Hardcoding exact colors instead of using a theme. | Making easy-to-read graphs. | Linked all charts to a central color theme so they match.
S4 | 2026-03-23 | 2026-03-26 | Mandavi Vaishya | Writing down simple explanations of how the app works. | Rushing bug fixes without checking them twice. | Making the screen look clean and professional. | Wrote a simple README guide and fixed the final text overlaps.