## Defect Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Mandavi Vaishya | 2026-03-03 | The app crashed because the Excel file had extra spaces in the column names. | Sprint 1 | Mandavi Vaishya | Logical | Added a step to automatically fix and clean the words before loading the data. | 2026-03-04 | Closed | Fixed the data loading issue completely.
2 | Mandavi Vaishya | 2026-03-10 | Ambulance dispatches were lost when the screen was reloaded. | Sprint 2 | Mandavi Vaishya | Logical | Added a feature to save the screen's memory to a file so it remembers. | 2026-03-11 | Closed | Data no longer disappears on refresh.
3 | Mandavi Vaishya | 2026-03-15 | Text on the department pie chart was squished together and hard to read. | Sprint 3 | Mandavi Vaishya | User Interface | Moved the text outside the chart circles and added more space so it fits nicely. | 2026-03-16 | Closed | Charts look clean and professional now.
4 | Mandavi Vaishya | 2026-03-18 | Some charts were not showing the right colors when the dark theme was turned on. | Sprint 3 | User Interface | User Interface | Adjusted the color settings so the charts are slightly see-through and easy to read. | 2026-03-18 | Closed | Dark mode works perfectly.
5 | Mandavi Vaishya | 2026-03-24 | Section titles were showing raw computer code instead of normal words on the screen. | Sprint 4 | Mandavi Vaishya | User Interface | Changed the code command to force it to show the text normally. | 2026-03-25 | Closed | Titles show up correctly without any code text.